## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | Database Security |  |  |  |  | Project Name: | Database Security
National Center: |  |  | <required> |  |  |  |  | National Center: | <required>
Project Manager Name: |  |  | <required> |  |  |  |  | Project Manager Name: | <required>
Project Description: |  |  | Create a database with at least 7 tables and 1000+ entries, 5 users. Use MySQL Workbench, and MySQL. Design and manage a project. |  |  |  |  | Project Description: | Create a database with at least 7 tables and 1000+ entries, 5 users. Use MySQL Workbench, and MySQL. Design and manage a project.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Open | High | Low | Yellow | EXAMPLE: Current project skill set may not be adequate to complete all project work. The current development team has been working in a Windows 2k environment, and the current requirements are for a LINUX environment. The project schedule would require 1500 development hours of a skilled LINUX operator, and approximately 1900 to 2200 if we retrain our current resources. | EXAMPLE: If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | EXAMPLE: Schedule approaches the required start date with no identification of required skill sets. | EXAMPLE: Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | EXAMPLE: Find internal resource that meets required skill set or train existing resources on LINUX. | EXAMPLE: Find resource that meets required skill set through external hiring sources.
2 | Open | High | Medium | Red | Communication: Ensuring effective communication between all members involved within the project to combat miss-communication. | If comunication is not in it's best practice the project will begin to slip. This will lead to miss-information and lack of inofmration to properly understand each task and remain on schedule. | Overall Project Failure | Goals and deadlines aren't met and everyone is on a different page. | Not establishing communication channels early on or not setting up meetings frequently enough. | Avoidance | Establish an effective route of communication and ensure all members are utilizing it to stay in contact. | Halt all operations and reconfigure with the members of the project and discuss the best way to stay connected and be able to have direct connection for propery ocmmunication.
3 | Open | High | Medium | Red | Identify an alternate for critical roles: Ensure that there is a backup person to take on a specific role if the primary worker falls ill or is unable to complete the task. The secondary and Primary must stay in communciation so they both understand what is going on. | If there is no contingency plan/backup for a critical role the project will see a halt in its schedule and additional funds will need to be outsourced to get the given task done by a 3rd party resource in order to remain within the project schedule. | Strategic | The primary gets sick or they are behind on their task. | Not identifying a backup or alternative within the company and outside the company. | Contingency | Identifty an alternative for an important task prior to starting it, one internal, a backup internal, and then an outside party. | Immediately look for an alternative personel for the role, if ubabkle to find someone then we will have a 3rd party vendor on hand.
4 | Open | High | High | Red | Version Control: Ensure change control through Github, everyone must have access to Github and be familiar with working with it. | Some employees working on the project will not be able to properly use the system or access the proper documents required for their system/software. The project will lack proper documentation and a system functionality. | Dependencies/Interoperability | Documents are not being pushed to Github and there are unknown changes to the project, out of order results. | Not agreeing on some form of version control, such as Github. A centralized location for monitoring changes and allowing for recall in the light of an error. | Avoidance | Establish specific versions of software that each member will utlize to ensure everyone is in agreeance and preventing compatability issues. | Halt all operations and reconfigure with the members of the project and discuss the best OS and other software versions to utilize so everyone owkring on the prioject has the same. Or, ensure the final projects results are all the same versions.
5 | Open | High | Low | Yellow | Backup Systems/Management: Github as a cloud based backup system. Ensure offline storage and configure another form of cloud backup. (Possibly Amazon AWS) | If anything were to happen to the system/database then everything would be lost since there is no back-up. | Data/Information | The system goes down and Github is having cyber attacks with loss of data. | Not establishng a backup system within a cloud and hard drive storage. If anything is lost It cannot be recovered. | Avoidance | Before the project begins establish an agreement on how the project will be backed up. In all of the following ways: two cloud based backups and one hard drive backup. | Immediately configure a backup process and initialze it to ensure the projects information/data is secured and backed up in case of an emergency or error.
6 | Open | Medium | High | Red | Group Software Compatability: Ensure team agrees on utlizing the same sotfware and OS systems. | Will lead to issues with version control, documentation, and a project that represents improper usage with multiple different depndencies. Errors will persist. | Dependencies/Interoperability | Members of the project are reciveving issues when trying to run similar things as they are not comaptible with eachother, updates are being pushed to Git with receieving end issues. | Not establishing a base for operating systems for each member of a team to utlize, such as all Ubuntu Linux. | Avoidance | Before the project begins come to an agreeance with all members on which Operating Systems to utlize to ensure 100% compatability. For example, everyone using Ubuntu Linux. | Halt all operations and reconfigure with the members of the project and discuss the best OS and other software versions to utilize so everyone owkring on the prioject has the same. Or, ensure the final projects results are all the same versions.
8 | Open | Medium | Medium | Yellow | Project Monitoring: Follow the project scope and include weekly (or daily) updates to ensure we are on schedule. If we fall behind we can easily update the schedule. It is always a good rule of thumb to list the completion of the project a few days prior to its deadline. | The project will not be completed on time. | Schedule | The project is behind on many tasks and the group is unaware of which takss are bhind shcedule, messing with subsequential flows. | Not effectivily monitoring the progress of a project and scheduling meetings to check up on tasks and their completion status. | Mitigation | Initialize a set of rules for properly monitoring the project. | Initialize an imediate meeting to discuss the project and progress thus far and continue to discuss the best meeting times and recongifure the understanding of the project and the importance of continous meetings for proper monitoring of the project.
9 | Open | Medium | Medium | Yellow | Proper Documentation: With each task provide adequete documentation so we can always refer back to it in the light of confusion or to better understand the process. Good documentation is vital as a turn in for projects. | The project will lack proof of work and lack resources and processes that were implemented to complete the project or task. | Project Resources | A task is completed without any documentation or only a few steps at the beginning, not showcasing how it was done. | No standard for documentation for groups to follow when documenting their task and its progress/process. | Avoidance | Discuss how all documents and tasks should be documented and provide each individual with the proper resources to do so. | Instruct all members to backtrack and properly document all tasks completed and to continue to do so on future tasks.
10 | Open | High | Low | Yellow | Scope Creep: Strictly discuss and follow the project scope, no unathorized changes mid-way through the project. | There will not be a clear understanding of the project in it's entirety and their will be unexpected changes that were not discussed and approved. The project risks being set back on scheddule and budget, leading to overall failure. | Project Management | Instead of completing a specific task in the scope their was an additional function added to the project, unathorized. | Not following the projects scope and previosuly discussed deadlines. There is talk about adding extra features. | Mitigation | Ensure everyone has a strong understanding of the project scope before getting started on the project. | Halt the project and call for a meeting to discuss any un authorized changes to the project and ime=mediately fix them and get the project scope back in alignment or discuss reasons for the change.
11 | Open | High | High | Red | Cost Risk: A shortage or mismanagement of project funds resulting from an inflated budget or other constraints is a threat to the project's completion. Monitor the projects budget to ensure minimal risk if funds need to be re-directed. | Funds will not be properly distributed and any changes to the initial budget are not able to be processed. The project risks completion or miantaining its life-cycle. | Life-cycle Costs | Additional funds had to be redistributed and the budget wasn't properly changed to accomadate these issues so now we ran out of money for the end tasks. | Not monitoring the budget and ensuring that everything is costing what it was expected to cost. | Mitigation | Strictly cover the budget and allow enough funds to be able to properly distribute them in case of an error or mishap. | Have backup funds or a place to go for additional fundings if possible. Consider what parts fo the project can be put on temporary hold in order to enable more fundings to complete the task that holds more importance or is half completed.
12 | Open | High | Medium | Red | Decision Gates: Review the schedule and requirements over again with the team. Ensure you are sticking to things and are progressing towards a successful project, this is where you can create changes that are discussed within the group. This is also where you test to ensure the project is meeting said requirements and functionality. | Changes necessary for the projects success are not discussed and implemented. The projects may lack specific requirements. | Feasibility | The project is behing and certain tasks and functionality are not meeting requirments. | Not establishing frequent meetings to discuss the rogress of the project and to test its fucntonality. | Avoidance | pre-set decision gate meeting times based on the scope to discuss and assess the project in its current form. | Review the schedule and requirements over again with the team. Ensure you are sticking to things and are progressing towards a successful project and submit any changes that may be beneficiary to the success of the project.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources